Case study

| Project , Activity: |  | Rites of Passage programme |
| --- | --- | --- |
| Client: |  | Learning & Skills Council (Young Peoples Learning Agency) |
| Value: |  | £120,000 |
| Contract Period: |  | May – September 2009 |
| Client’s Requirements: Services Required |  | Transformational program for young Afro-Caribbean NEET male and females to encourage them to consider an alternative lifestyle and get back into education, employment, or training. |
| ACBC Role and Contribution |  | - Design programme to meet client needs. - Delivery of programme in 1 x weekly sessions over 13 weeks. - Demonstrate a different perspective of their lives. - Show them possibilities and opportunities for a different way of life. - Encourage them to adopt a lifestyle away from crime and anti-social behaviour on their release. |
| Problems / issues encountered and resolved |  | - Recruitment of hard to reach young people – we adapted and extended the recruitment procedures to overcome these problems. - Negative attitude of some participants – we challenged their attitudes and behaviour by allowing them to express their creative talents. - Low self esteem and aspirations of participants – we encouraged positive values among participants by showing them how they can succeed and the benefits of an alternative lifestyle. - Difficult relationships with other people –we had to convince them of the value of the conflict resolution and the negative effects of gang culture. . |
| Outcomes achieved |  | - 40 started the course 16 completed the course. Other were imprisoned during the course or did not wish to continue with the program. 2 obtained employment while on the program. - All participants produced positive feedback - All16 participants that completed the program signed on at colleges to start further education courses in October 2009. |

Testimonial:

Participant	“ the experience has given me more confidence and made inroads to 		raising my self-esteem. I enjoyed the audio visual side to the 			programme and especially welcomed the videos on how to escape the 		gang structure”.