Case study

| Project , Activity: |  | Research Report on the ‘Needs’ of young BME people in the Manchester Youth Offending Service. |
| --- | --- | --- |
| Client: |  | Manchester Youth Offending Service /Manchester City Council |
| Value: |  | £10,000 |
| Contract Period: |  | July 2009 – May 2010 |
| Client’s Requirements: Services Required |  | A report to inform the development and programmes and interventions for young BME people under the supervision of the Manchester Youth Offending Service. |
| ACBC Role and Contribution |  | - Design and develop the research methodology. - Examine the differential treatment of the young BME people by the Criminal Justice system - Examine programmes and interventions that can assist the young BME people from entering and not to re-enter the Criminal Justice system. - Examine the possibilities and opportunities for the young BME people to take up a different way of life - Examine alternative approaches to offending behaviour. - Encourage and to empower the young BME people to adopt a lifestyle away from crime and anti-social behaviour. - Explore the range and distinct but interrelated factors that impacts upon the experiences of the young BME people - Explore the contemporary approaches of engaging the hard to reach young BME people. |
| Problems / issues encountered and resolved |  | - Initial reluctance to speak to researchers, due to lack of trust – we employed known intermediaries to overcome this problem. - Negative attitude of some participants – we challenged attitudes and behaviour - Low self esteem and aspirations of participants – we encouraged positive values among participants. - Concerns that their involvement and responses will have 'comebacks' against them – assured the BME young people their responses will be confidential and the recorded interviews destroyed on completion of the report. |
| Recommendations (in brief): |  | - Implement routine monitoring of YOS practice by ethnicity. - Consider the relationship between the quality of assessments (pre-sentence report and Asset) undertaken on BME young people and their sentence outcome. - Develop an understanding for the contributory factors that results in higher rates of young BME people being supervised by Manchester YOS. - .Initiate dialogue with sentencer's to identify reasons for and remedies for the increased likelihood for custodial sentences for young BME people. - To undertake a more in-depth investigation of BME sentencing decisions. - Design program for empowerment of young BME people. |